## Instructions
PROJECT TASK TRACKER - DAILY, DATE-WISE
HOW THIS WORKBOOK WORKS
1. Enter every task ONCE on the 'Task Log' sheet. Never retype a task on a new day.
2. Fill only the coloured columns. White columns are formulas - do not type in them.
3. If a task is not marked Completed by its Due Date, it is carried forward automatically:
its 'Active Date' rolls to today and it keeps appearing on 'Today's Plan'.
4. Set Status = Completed and enter the Completed Date - the task closes on that date
and stops rolling forward.
5. 'Dashboard' is live. Every count and chart recalculates on its own.
TWO DIFFERENT DATES - USE BOTH
Due Date - when YOUR step has to be finished (send quote, prepare kit, follow up DGCA).
Execution / Event Date - the committed date the project itself must happen: the demo date,
dispatch date, inspection date, tender submission deadline, training batch start.
This is the date you cannot miss in front of the client. Pair it with Event Type.
'Days to Event' counts down for you and turns red once the date has passed.
A task can have a due date only, an event date only, or both.
COLUMNS YOU FILL
Date Logged / Vertical / Task Description / Client / Order Type / Priority
Due Date / Execution-Event Date / Event Type / Status / Completed Date / Remarks
Shortcut for any date cell: press Ctrl + ; (inserts today's date)
COLUMNS CALCULATED FOR YOU (do not edit)
Active Date - the date the task sits on today. Completed tasks freeze on their completion
date; open tasks roll to TODAY once the due date has passed.
Day Status - Completed / Carried Forward / Due Today / Upcoming
Days to Event - days remaining to the execution date. Negative means the date has passed.
Ageing (Days) - how long the task has been alive
Open Seq - internal helper for 'Today's Plan'. Leave it alone (you may hide column Q).
Assigned To - who's doing the task (type a name; not auto-filled). Column S — added at
the end on purpose so it never shifts the formula columns above.
SHEETS
Task Log - master register of every task, all verticals
Projects - one row per project: name, requirements, dates, stage checklist, % complete
Today's Plan - everything open as on today, including carry-forwards
Dashboard - counts, completion %, upcoming events, and 5 charts
PROJECTS — L1 TO PAYMENT TRACKING
1. On the 'Projects' sheet, enter a Project ID (your own numbering, optional), Project Name,
Vertical, a short Requirements line, Start Date, End Date.
2. For each stage column (L1, BOQ, TEC, Awarded, Procurement, Inventory, Production, QC,
Testing, Dispatch, Delivered, Payment, Documentation, Failed) pick 'Pending' if that stage
this project, or leave it blank if it doesn't. This is your one-time stage selection.
3. As work progresses, change a stage's value from 'Pending' to 'Done' when it's finished.
4. '% Complete' and 'Overall Status' recalculate on their own — done stages ÷ stages you picked.
Marking 'Failed' = Done sets Overall Status to Failed regardless of the other stages.
5. The app's Projects tab does the same thing with tap-to-select stages and tap-to-complete chips —
whichever you edit (Excel/Sheet or app), use Export/Import (see below) or Google Sheets live
sync to keep the other one matching.
NOTES
- 6 sample rows are pre-filled so you can see the format. Delete rows 2-7 before real use.
- Formulas run to row 500. To extend, select the last filled row and drag down.
- Task ID on Task Log is a simple running row order in this offline file. The app and the
live Google Sheet instead reset it to 1 every day (carried-forward tasks first) — that
day-aware numbering isn't practical to reproduce with plain Excel formulas, so treat this
file's Task ID as a stable reference number, not the same as what you'll see in the app.
- The web app uses these exact columns, so Excel and the app import/export cleanly.

## Task Log
Task ID | Date Logged | Vertical | Task Description | Client / Customer | Order Type | Priority | Due Date | Execution / Event Date | Event Type | Status | Completed Date | Active Date | Day Status | Days to Event | Ageing (Days) | Open Seq | Remarks | Assigned To
| 2026-09-09 | Tenders | Submit technical bid documents for surveillance drone tender | State Police Dept | Tender / Bid | High | 2026-09-13 | 2026-09-19 | Tender Submission | In Progress | [6 empty] | SAMPLE - overdue step, carried forward automatically
| 2026-09-11 | Defence | Arrange flight demo of VTOL unit for evaluation team | MoD - Army Wing | Drone Sale - Govt Order | High | 2026-09-15 | 2026-09-21 | Demo | In Progress | [6 empty] | SAMPLE - demo date is the committed date
| 2026-09-11 | RPTO Establishment | Follow up DGCA file for new RPTO site approval | Internal | Internal / Admin | Medium | 2026-09-18 | 2026-10-06 | Go-Live | Not Started | [6 empty] | SAMPLE
| 2026-09-07 | Agri Services | Schedule spraying crew for 120 acre paddy block | Farmer Producer Org | Service / DaaS | Medium | 2026-09-10 | 2026-09-10 | Site Survey | Completed | 2026-09-10 | [5 empty] | SAMPLE - closed, stops rolling
| 2026-09-13 | Redington | Share updated price list and channel margin sheet | Redington India | Drone Sale - Private | Low | 2026-09-20 |  |  | Not Started | [6 empty] | SAMPLE - no event date, only a due date
| 2026-09-14 | DaaS | Raise invoice for September survey mandays | Private Infra Co | Service / DaaS | High | 2026-09-16 | 2026-09-17 | Payment / Invoice | In Progress | [6 empty] | SAMPLE
Formulas:
Active Date = IF([Task Description]="","",IF([Status]="Completed",IF([Completed Date]="",[Due Date],[Completed Date]),IF([Due Date]="","",IF([Due Date]<TODAY(),TODAY(),[Due Date]))))
Day Status = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Due Date]="","No Due Date",IF([Due Date]<TODAY(),"Carried Forward",IF([Due Date]=TODAY(),"Due Today","Upcoming")))))
Days to Event = IF([Task Description]="","",IF([Execution / Event Date]="","",IF([Status]="Completed","",[Execution / Event Date]-TODAY())))
Ageing (Days) = IF([Task Description]="","",IF([Date Logged]="","",IF([Status]="Completed",IF([Completed Date]="","",[Completed Date]-[Date Logged]),TODAY()-[Date Logged])))

## Projects
Project ID | Project Name | Vertical | Requirements | Start Date | End Date | L1 | BOQ | TEC | Awarded | Procurement | Inventory | Production | QC | Testing | Dispatch | Delivered | Payment | Documentation | Failed | % Complete | Overall Status
PRJ-001 | VTOL Unit — MoD Surveillance Order | Defence | 20kg payload VTOL, thermal + EO camera, 2hr endurance | 2026-09-01 | 2026-12-15 | Done | Done | Done | Done | Pending
PRJ-002 | Agri Drone Batch — Redington Channel | Redington | 6 units, spraying config, dealer training included | 2026-08-15 | 2026-10-10 | Done | Done | Done | Done | Done | Done | Pending |  |  |  |  | Pending | Pending

## Today's Plan
TODAY'S PLAN - every open task as on
Auto-generated from the Task Log. Overdue tasks stay here until marked Completed. Nothing to type on this sheet.
S.No | Vertical | Task Description | Client / Customer | Priority | Due Date | Event Date | Event Type | Days to Event | Status | Day Status | Ageing (Days)

## Dashboard
PROJECT TASK DASHBOARD
SNAPSHOT
Total Tasks
Completed
Open
Carried Forward
Due Today
Events in next 7 days
Event Dates Missed
Completion %
TASKS BY VERTICAL |  |  |  | TASKS BY STATUS |  | LAST 14 DAYS - DUE vs COMPLETED |  |  | UPCOMING EVENTS (NEXT 30 DAYS)
Vertical | Total | Completed | Open | Status | Count | Date | Tasks Due | Completed | Event Type | Count
Defence |  |  |  | Not Started |  |  |  |  | Demo
Industry |  |  |  | In Progress |  |  |  |  | Delivery / Dispatch
Tenders |  |  |  | On Hold |  |  |  |  | Inspection
RPTO |  |  |  | Completed |  |  |  |  | Tender Submission
RPTO Establishment | [8 empty] | Training Batch
DaaS | [8 empty] | Site Survey
V V Yatra |  |  |  | OPEN TASKS BY PRIORITY |  |  |  |  | Go-Live
Redington |  |  |  | Priority | Open |  |  |  | Review Meeting
CoE |  |  |  | High |  |  |  |  | Payment / Invoice
Global |  |  |  | Medium |  |  |  |  | Other
Agri Drone |  |  |  | Low
Agri Services
Note: counts read Task Log rows 2-500. 'Carried Forward' = not completed and past its due date. 'Event Dates Missed' = execution date passed with the task still open.
Formulas:
Count = COUNTIFS('Task Log'!$J2:J500,[UPCOMING EVENTS (NEXT 30 DAYS)],'Task Log'!$I2:I500,">="&TODAY(),'Task Log'!$I2:I500,"<="&(TODAY()+30),'Task Log'!$K2:K500,"<>Completed")